## Section Title & Team
Section | A
Title | Online Examamination Portal
Team Lead | Subhadeep Dash | S20160010021
Members | Anirudh Kannan V P | S20160010005
| Sai Vamshi S D | S20160010080
| Parkhi Mohan | S20160010061
| Sree Pragna V | S20160010106
| Mounika Chadalavada | S20160020117

## Work Tracking
Project Level | Week 5/ 6th Sept 2018 |  |  | Week 4/ 31st Aug 2018 |  |  | Week 3/ 24th Aug 2018 |  |  | Week 2/ 17th Aug 2018 |  |  | Week 1/ 10th Aug 2018
| Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges
Feedback received on project | Rectifying risks, Preparation of Gantt chart | Last Feedback changes update | Changing already designed diagrams to a newer one with hierarchy suggested | Draw ER diagram, Activity diagram, User case diagram and fill sample data into tables | Completed all the scheduled tasks and have been verified by the evaluator | Preparing a well structured design of the upcoming project | Project idea and the corresponding use case diagram
Refactor Status
Team Work Breakdown Structure
Subhadeep Dash | Change of ER diagram | Changed Successfully | Making the diagram vivid and understandable | ER diagram to be drawn | Designed ER diagram successfully | Proper ER diagram displaying all details
Anirudh Kannan V P | Technical Requirements | Technical Requirements | Deciding Technical Requirements once again | Technical Requirements | Technical Requirements | Deciding Technical Requirements
Sai Vamshi S D | Sample Data Filling | Sample Data Filling | Filling Appropriate data as per new tables | Sample Data Filling | Sample Data Filling | Filling appropriate data as per tables designed
Parkhi Mohan | Designing of Gantt Chart
Sree Pragna V | Preparing of Gantt Chart
Mounika Chadalavada

## Work Products
Project Level | Week 4/ 31st Aug 2018 |  |  | Week 3/ 24th Aug 2018 |  |  | Week 2/ 17th Aug 2018 |  |  | Week 1/ 10th Aug 2018
| Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges | Tasks Scheduled | Tasks completed | Challenges
Feedback received on project
Refactor Status
Team Work Breakdown Structure
Subhadeep Dash
Anirudh Kannan V P
Sai Vamshi S D
Parkhi Mohan
Sree Pragna V
Mounika Chadalavada

## Sample Data
User
user_id(pk) | user_name | phone | email | password | account_type | created | modified
1 | Subhadeep Dash | 9010128249 | subhadeep.d16@iiits.in | 0b8008dabf1b6e30a3107afd7b2b505e | 1 | 2018-07-05 11:55 | 2018-08-25 05:19
2 | Subrabala Dash | 9912786500 | subrabala.dash@gmail.com | 0b8008dabf1b6e30a3107afd7b2b505e | 0 | 2018-07-05 11:55 | 2018-07-28 02:30
3 | Sai Krishna | 8653415675 | user@ennoble.com | cc03e747a6afbbcbf8be7668acfebee5 | 1 | 2018-07-28 16:32 | 2018-07-28 16:32
4 | Sai Srehan | 7680927547 | saisrehan@gmail.com | e10adc3949ba59abbe56e057f20f883 | 1 | 2018-07-28 16:46 | 2018-07-28 16:46
Subjects
subject_id(pk) | subject_name | description | created | modified
1 | AI | Artificial Intelligence | 2018-07-05 11:55 | 2018-08-25 05:19
2 | DBMS | Database Management System | 2018-07-05 11:55 | 2018-07-28 02:30
3 | CP | Computer Programming | 2018-07-28 16:32 | 2018-07-28 16:32
4 | LS | Life Sciences | 2018-07-28 16:32 | 2018-07-28 16:32
Quiz_details
quiz_id(pk) | q_name | duration | no. of questions | attempts_allowed | pass_percentage | subject_id(fk) | created | modified
1 | Mid Sem-1 | 3:00 | 10 | 1 | 30 | 1 | 2018-07-05 11:55 | 2018-08-25 05:19
2 | Mid Sem-1 | 3:00 | 10 | 1 | 30 | 4 | 2018-07-05 11:55 | 2018-08-25 05:19
3 | Mid Sem-2 | 3:00 | 10 | 1 | 30 | 3 | 2018-07-05 11:55 | 2018-07-28 02:30
4 | End Sem | 3:00 | 20 | 1 | 30 | 2 | 2018-07-28 16:32 | 2018-07-28 16:32
Topic
topic_id(pk) | topic_name | created | modified
1 | Machine Learning | 2018-07-05 11:55 | 2018-08-25 05:19
2 | Data Structures | 2018-07-05 11:55 | 2018-07-28 02:30
3 | Basics of DBMS | 2018-07-28 16:32 | 2018-07-28 16:32
4 | Zoology | 2018-07-28 16:32 | 2018-07-28 16:32
Subtopic
Subtopic_id(pk) | subtopic_name | topic_id(fk) | created | modified
1 | Principal Component Analysis | 1 | 2018-07-05 11:55 | 2018-08-25 05:19
2 | Pointers | 2 | 2018-07-05 11:55 | 2018-07-28 02:30
3 | Overview of DBMS | 3 | 2018-07-28 16:32 | 2018-07-28 16:32
4 | Blood Groups of Humans | 4 | 2018-07-28 16:32 | 2018-07-28 16:32
Level
level_id(pk) | level_name
1 | Easy
2 | Intermediate
3 | Advanced
Registration
registration_id(pk) | user_id(fk) | exam_id(fk) | attempt_no | registered | answered | view_answers | created
1 | 1 | 1 | 1 | 1 | 1 | 1 | 2018-08-25 05:19
2 | 2 | 2 | 1 | 1 | 0 | 0 | 2018-07-28 02:30
3 | 3 | 3 | 1 | 0 | 1 | 1 | 2018-07-28 16:32
4 | 4 | 4 | 1 | 1 | 1 | 1 | 2018-07-28 16:46
Question
question_id(pk) | question | description | question_type(fk) | score | exam_id | subtopic_id | created | modified
1 | What is full form of PCA? | AI based | 1 | 10 | 1 | 1 | 2018-07-28 16:32 | 2018-07-28 16:32
2 | What is a pointer ? | CP based | 5 | 20 | 3 | 2 | 2018-07-29 16:32 | 2018-07-29 16:32
3 | What is the full form of DBMS | DBMS based | 4 | 10 | 4 | 3 | 2018-07-30 16:32 | 2018-07-30 16:32
4 | If parents have O+ and B+, what are the possible blood groups a child would possess? | Life Sciences | 2 | 10 | 2 | 4 | 2018-07-30 16:32 | 2018-07-30 16:32
Question_type
type_id(pk) | type
1 | Multiple Choice Single Answer
2 | Multiple Choice Multiple Answer
3 | Match the Columns
4 | Short Answer
5 | Long Answer
Options
Option_id(pk) | question_id(fk) | option_no | option_value
1 | 1 | 1 | Part of Component Analysis
2 | 1 | 2 | Principle Component Analysis
3 | 1 | 3 | Per Capita Annum
4 | 1 | 4 | Principle Component Amount
5 | 4 | 1 | O+
6 | 4 | 2 | B+
7 | 4 | 3 | A+
8 | 4 | 4 | AB+
Answers
answer_id(pk) | question_id(fk) | answer
1 | 1 | 2
2 | 2 | A pointer is a variable whose value is a direct access of the memory variable
3 | 3 | Database Management System
4 | 4 | 1
5 | 4 | 2
Results
result_id(pk) | question_id(fk) | answer | score | registration_id(fk) | verify
1 | 1 | Part of Component Analysis | 0 | 1 | 1
2 | 2 | A pointer is a pointer | 0 | 1 | 0
3 | 3 |  | 0 | 1 | 0
4 | 4 | O+;AB+; | 0 | 1 | 1
5 | 1 | Principle Component Analysis | 10 | 2 | 1